## ITT
Fram indicator | Target | Completed | Progress (%) | Status
Number of households that received seed kits and grant | 500 | 450 | 90% | On the right track
The percentage of benficiaries who expressed satisfaction with the process | 80% | 85% | 106% | The target has been exceeded
Precentage of households that successfully resumed production | 75% | 70% | 93% | On the right track

## CRM
Case ID | Date Received | Feedback Type | Channel | Description | Assigned To | Action Taken | Status
CRM-KRT-001 | 2026-06-15 | Query | Hotline | Beneficiary asking about the best depth to plant the distributed vegetable seeds. | FSL Technical Team | Agricultural specialist called back and provided planting instructions. | Resolved
CRM-KRT-002 | 2026-06-15 | Query | Field Staff | Inquiring about the optimal watering schedule for the crop kits during summer. | FSL Technical Team | Standard irrigation guideline sheet shared with the community leader. | Resolved
CRM-KRT-003 | 2026-06-16 | Query | Hotline | Beneficiary asking if the small livelihood grant can be spent on repairing water pumps. | FSL Technical Team | Confirmed that tool repair is an eligible expenditure under project guidelines. | Resolved
CRM-KRT-004 | 2026-06-16 | Query | Suggestion Box | Requesting information on whether there will be a second round of seed distribution. | FSL Technical Team | Informed the beneficiary that this is a one-time distribution per baseline criteria. | Resolved
CRM-KRT-005 | 2026-06-17 | Query | Hotline | Inquiring if organic fertilizers can be mixed with the provided soil kit. | FSL Technical Team | Technical team provided safe mixing ratios to prevent root damage. | Resolved
CRM-KRT-006 | 2026-06-17 | Query | Field Staff | Asking about signs of seed spoilage before planting. | FSL Technical Team | Explained quality check signs; verified his kit was completely healthy. | Resolved
CRM-KRT-007 | 2026-06-18 | Query | Hotline | Beneficiary asking for alternative tools as they already own the distributed kit tools. | FSL Technical Team | Explained that kits are standardized; but they can utilize cash grants for other tools. | Resolved
CRM-KRT-008 | 2026-06-19 | Query | Hotline | Inquiring about the expected harvest timeline for tracking indicators. | FSL Technical Team | Provided the average 60-90 days timeline for the distributed crop types. | Resolved
CRM-KRT-009 | 2026-06-20 | Query | Suggestion Box | Asking if multi-household farming groups can pool their cash grants together. | FSL Technical Team | Welcomed and approved the collective group-farming approach. | Resolved
CRM-KRT-010 | 2026-06-15 | Complaint | Field Staff | Beneficiary reported sudden security checkpoint delays blocked access to the site. | MEAL Team | Documented in lessons learned to establish closer distribution nodes next time. | Referred
CRM-KRT-011 | 2026-06-15 | Complaint | Hotline | Elderly beneficiary complained about the lack of transport support to move the kit home. | MEAL Team | Shared feedback with program team to include localized transport stipends in future budgets. | Referred
CRM-KRT-012 | 2026-06-16 | Complaint | Field Staff | High crowd density at the main gate caused long waiting times under the sun. | MEAL Team | Recommended decentralized time-slots per neighborhood for the upcoming distributions. | Referred